## Introduction
Environment Strategy Delivery Plan The Environment Strategy for West Berkshire has been refreshed for the period 2025 - 2030. Alongside updating and refocusing the strategy, the Delivery Plan has also been refined and prioritised to fit with the refreshed strategy. The tabs in this Delivery Plan each cover a different key theme and contain relevant overarching actions and specific tasks to help achieve them.
This Delivery Plan will be updated at least every quarter. As new opportunities arise that fit with the priorities for delivery and offer good value for money, additional tasks will be added.
The key themes that structure the Delivery Plan are:
Energy Efficiency and Renewables
Sustainable Transport
Natural Environment
Waste Reduction and Recycling
There are common threads that link across all the themes and these are explained in the tab following the themes.
Lastly, a list of other strategies, plans and documents that this Environment Strategy Delivery Plan links with are included in the final tab.
For queries relating to the Environment Strategy Delivery Plan, please email: Environment@westberks.gov.uk
Last updated March 2026.

## Energy Efficiency & Renewables
Theme | Overarching Action | Specific Tasks | Progress | Responsibility | Estimated timescale | Estimated carbon reduction (tCO2e) | Estimated cost | Net Zero Target contribution WBC/District/ Both
Energy Efficiency & Renewables | Work with partners to ensure good strategic planning in support of decarbonisation goals | (EER1)Progress a review of the Local Area Energy Plan and increase partnership working with neighbouring authorities. | In progress | WBC Environment Delivery Team | To be reviewed in 2025/6 | TBC depending on the nature and size of projects. | £(up to 25k ) | Both
|  | (EER2) Improve links with SSEN (Scottish & Southern Electricity Network) through regular engagement and use of bespoke planning tools | In progress | WBC Environment Delivery Team | Ongoing | N/A Enabling Project | Officer time | N/A
| Progress the decarbonisation of the Council's estate and activities | (EER3) Conduct further audits of the Council's buildings to: a) assess energy efficiency b) identify areas for improvement (e.g. develop Decarbonisation Plans) c) bid for funding and d) undertake projects to improve energy efficiency | In progress | WBC Property/WBC Environment Delivery Team/ Team/WBC Leisure Team | Ongoing- Longterm Project | TBC depending on the nature and size of projects. | ££££ (over £0.5m) | WBC
| Deliver projects to generate renewable energy | (EER4) Install a large scale solar farm near Grazeley | In progress | WBC Environment Delivery Team | Delivery in 2025/26 | 3747-3646 tCO2e/year | ££££ (Over £0.5m) | Both
|  | (EER5) Initiate, plan and deliver further projects to install renewable energy on existing council assets and properties | In progress | WBC Environment Delivery Team/WBC Property Team/WBC Leisure Team/ WBC Education Team | Main delivery phase 2024/25 -2027/28 | 71-580 tCO2e/year - currently this is based on solar PV but can be adjusted as and when WBC introduces other renewables. | ££££ (Over £0.5m) | WBC
| Continue to develop good communications and partnership working to assist residents, communities. schools and businesses to become more energy efficient and decarbonise their activities. | (EER6) Work with stakeholders and support community groups, to ensure they have access to relevant funding to develop community proposals for the installation of renewable technology | In progress | WBC Environment Delivery Team | Ongoing | 3-15 tCO2e/year - this is based on installing 25kWp of Solar pv by the end of 2024/25 financial year and each year beyond that 50kWp is installed. | Officer time | District
|  | (EER7) Providing landlords and home owners with advice on funding to improve energy efficiency and affordability (with a particular focus on properties where EPC (Energy Performance Certificates) are E or below) | Not started | WBC Environment Delivery Team/Housing Service | Ongoing | 31 -127 tCO2e/year Assumes that E,F & G private rental accommodation is brought up to D standard. | Officer time | Both
|  | (EER8) Support residents to assist with energy switching and group buying schemes to ensure they have the most affordable tariffs and opportunities for good value green energy initiatives | In progress | WBC Environment Delivery Team/Housing Service | Ongoing | Low/Medium | Officer time | District

## Sustainable Transport
Theme | Overarching Action | Specific Tasks | Progress | Responsibility | Estimated timescale | Estimated carbon reduction (tCO2e) | Estimated cost | Net Zero Target contribution WBC/District/ Both
Sustainable Transport | Work with Partners to develop strategic plans and initiatives to support sustainable and low carbon travel across the District | (ST1) Develop the next Local Transport Plan for the district | Complete | WBC Environment Delivery Team/ Network Management | Summer 2025 | N/A Enabling Action | £££ (£100k to £0.5m) | N/A
|  | (ST2) Deliver the actions as identified within the Council's ULEV Strategy, including ensure 100% of the Council's (viable) light fleet vehicles uses ULEV by 2030 | In progress | Various WBC Teams | By 2030 | 66 -264 tCO2e/year (average reduction) based upon fleet transitioning to EV | ££££ (Over £0.5m) | Both
|  | (ST3) Expand car club activities to deliver vehicle locations in 3 new areas of the District (in addition to Newbury town already being served) by 2030 with a priority of using EVs wherever possible. | In discussion | Environment Delivery Team | By 2030 | TBC | TBC | Both
|  | (ST4) Delivery of plans under relevant contracts to provide EV chargepoints in identified community areas to support residents and businesses switching to EVs NB: Concession contract being considered April / May 2025 - Task may be updated as a result | New 20-year contract being considered April / May 2025 | Environment Delivery / Network Management Teams | Figure and timescale to be set once new contract is confirmed | TBC | TBC | Both
| Through effective communication and engagement promote sustainable travel options | (ST5) Encourage residents and visitors to use public transport by providing up to date information on bus and train routes and providing incentives where possible. In line with the Bus Service Improvement Plan. | TBC this is a new action | Transport Services/ WBC Environment Delivery Team | Ongoing | 2775 tCO2e/year (This is based on the previous action and will need to be revised.) | ££££ (over £0.5m)TBC. We will receive funding | District
| Effective use of travel plans and travel monitoring systems to inform future sustainable travel decisions | (ST6) Install a network of automatic active travel monitoring sites at key locations on the LCWIP (Local Cycle and Walking) Infrastructure primary network | In progress | WBC Network Management | TBC as there are new sites | N/A Enabling Action | ££ (25k - £100k) | N/A
| Work with partners to develop active travel routes and hubs across the District | (ST7) Delivery of the priority routes identified in the Local Cycle and Walking Infrastructure Pla)(LCWIP) | In progress | WBC Network Management | Medium term (April 2023- March 2026) | Low/ Medium | The Council's Capital Programme details the funding allocated to delivery of active travel routes and will be enhanced by further grant funding where opportunities arise. | District
|  | (ST8) Deliver a Cycle Hub in Theale and investigate further sites. | In progress | WBC Environment Delivery Team/ GWR | Medium term (April 2023- March 2026) | Low | £££ (£100k- £ 0.5m) | District
| Develop Sustainable Travel initiatives for Council staff | (ST9) Implement a new travel policy for staff to incentivise more sustainable patterns of travel to/from work and on site visits | Delayed | WBC Environment Delivery Team | Short term (this is behind schedule). | Medium | ££ (25k - £100k) | WBC

## Natural Environment
Theme | Overarching Action | Specific Tasks | Progress | Responsibility | Estimated timescale | Estimated carbon reduction (tCO2e) | Estimated cost | Net Zero Target contribution WBC/District/Both
The Natural Environmnet | Develop and implement a strategic approach to the creation of Natural Capital across the District | (NE1) Continue to develop a Green and Blue Infrastructure (GBI) Framework to investigate an approach to natural regeneration to identify opportunities for rewilding, tree planting, CO2 capture and habitat conservation and creation across West Berkshire. | In progress | WBC Countryside Team and WBC Environment Delivery Team | Ongoing | N/A Enabling Action | £££ ( £100k - £0.5m) | Both
|  | (NE2) Through the Natural Solutions Delivery Partnership (NSDP) continue to work with key stakeholders across the district on developing opportunities for habitat creation and natural capital initiatives. | In progress | WBC Countryside Team and WBC Environment Delivery Team | Ongoing | N/A Enabling Action | Officer Time | N/A
|  | (NE3) Develop an approach and deliver projects that will achieve the amount of Nutrient Mitigation in the River Lambourn Catchment Area required by the grant funding received through the Local Nutrient Mitigation Fund | In progress | WBC Environment Delivery Team, Drainage Team, Planning and Ecology | 2025 - 2027 | Unknown as yet | TBC | Both
|  | (NE4) Engage and contribute to the development of the Berkshire Local Nature Recovery Strategy (LNRS) to establish a regional approach to nature recovery. | In progress | WBC Countryside Team and WBC Environment Delivery Team | 2025/26 | N/A Enabling Action | Officer Time | Both
| Working with partners, continue to develop and implement best practice methods of environmental land and water management. | (NE5): 'Work with partners to develop Natural Flood Management (NFM) projects to allow catchment wide adaptation to flooding. | In progress | Various WBC Teams and the Environment Agency | April 2026- March 2030 | N/A | Officer Time | NA
|  | (NE6): Ensure hedgerow management on all council land is in accordance with good ecological practice guidance. | In progress | WBC Countryside Team | Ongoing | Low | £ (up to £25k) | District

## Waste Reduction & Recycling
Theme | Overarching Action | Specific Tasks | Progress | Responsibility | Estimated timescale | Estimated carbon reduction (tCO2e) | Estimated cost | Net Zero Target contribution WBC/District/Both
Waste Reduction & Recycling | Continue to develop the actions to reduce municipal waste and increase recycling rates | (WRR1) Reuse, recycle and compost at least 60% of municipal waste we handle by 2030. | In progress | WBC Waste Management | Long term (April 2026- March 2030). | 161 tCO2e per year | TBC, awaiting more information from central government. | District
|  | (WRR2) Implement a kerbside collection system that is fully compliant with the minimum service standards required by the UK Government. | In progress, (must be complete by 31st March 2026). | WBC Waste Management | By March 2026 | Medium | ££££ (Over £0.5m) | District
|  | (WRR3) Encourage residents to consider how changes might be made to their own recycling habits so that the amount of waste unnecessarily sent to landfill is minimised. | In progress | WBC Waste Management Key support from Waste Minimisation Officer | Ongoing | Low/ Medium | Officer Time | District
| Reduce waste and increase recycling rates from Council activities | (WRR4) Work to reduce waste and increase the recycling rate of WBC's offices via improved awareness of the recycling scheme and provision of improved facilities where required. | In progress | Facilities Management/Environment Delivery (Comms assistance) | Ongoing | Low/ Medium | £ (up to £25k) | WBC

## Common Threads
There are a number of aims or approaches that are relevant to all the themes identified in the Environment Strategy / Delivery Plan. These are therefore identified as common threads. A brief explanation of each of the 5 common threads across all themes is given below along with some examples of how we deliver these threads and other relevant key links.
Common Thread | Explanation | Examples of relevant work/ links to relevant documents
Net Zero | Net zero is a position the Council seeks to achieve for its own activities by 2030. There is also a commitment to assist in the achievement of net zero for the District. This is a larger task and will involve all individuals, communities, organisations and businesses playing their part. Many of the schemes, projects and actions across all the themes will contribute in some way to the Council reducing its carbon impact or to the reduction of the District's carbon footprint. | Solar PV Grazeley- Webpage / HVO/
Health and Wellbeing | Many actions under the themes of the Delivery Plan will have a positive impact on health and wellbeing. Whether this is through reduced emissions from transport creating cleaner air, or enhancement of and greater access to nature, we aim to improve health and wellbeing through our activities and guard against any detrimental impacts. This supports the Council's commitment to a 'health in all policies' approach across the organisation. | Berkshire West Health and Wellbeing Strategy 2021-2030 - West Berkshire Council
Communications | Communication is key to working effectively. The Council will seek to communicate effectively and in a variety of ways to ensure residents, communities, organisations and businesses are aware of our plans and proposals. The importance of communicating successes of our own and others is recognised as an important way of encouraging others with ideas and inspiration. We will also seek to learn from others who communicate their innovative projects and help us to improve our projects and plans. | Environment Newsletter (monthly) Press releases Green Hub on Website
Partnerships | West Berkshire Council seeks to work in partnership wherever possible, particularly where this will strengthen outcomes, make the best use of resources and support, build and encourage community action. Existing partnership working has delivered some excellent outcomes and opportunities for new partnerships are encouraged. | BBOWT West Berkshire Natural Solutions Delivery Partnership
Education and Engagement | Providing information to help increase knowledge on climate and sustainability matters across the themes is important to enable and encourage understanding leading to action and behavioural change. Opportunities for engagement to support this education and joint learning are built into the Council's work alongside a desire to take up new opportunites for engagement where they deliver on important objectives and priorities. | Town and Parish Council Climate Forum https://www.westberks.gov.uk/parish-climate-forum Environment Advisory Group Open Forum Eco Champions (Internal)

## Relevant Documents
Publication: | Link/ Notes:
The Environment Strategy | https://www.westberks.gov.uk/media/49068/Environment-Strategy-2020-2030/pdf/Environment_Strategy_2020-2030_updated.pdf?m=1615892303337%20%20Refreshed%20Strategy%20due%20to%20be%20published%20May%202025
WBC Ultra Low Emissions Vehicle Strategy | Refreshed strategy due to be published Summer 2025
Local Area Energy Plan | Summary version available
Local Transport Plan | https://www.westberks.gov.uk/media/64415/Local-Transport-Plan-4/pdf/Local_Transport_Plan_4_2025-2040_1dnucpo31hhpu.pdf?m=1755792202317
Bus Service Improvement Plan | https://www.westberks.gov.uk/media/57563/Bus-Service-Improvement-Plan-2023/pdf/West_Berkshire_Council_Final_BSIP_2023.pdf?m=1699346886323
Flooding Be Prepared! Leaflet | https://www.westberks.gov.uk/media/57946/Flood-Booklet/pdf/Flood_Booklet.pdf?m=1704368266770
Social Value Policy | https://intranet/media/51707/Social-Value-Policy/pdf/Social_Value_Policy_20211.pdf?m=1710415437047
West Berkshire Vision 2026 (refreshed 2023) | https://www.westberks.gov.uk/media/46989/West-Berkshire-Vision-2036-2019/pdf/WBV_2036_final_19.pdf?m=636903249717100000
The Council Strategy | https://intranet/media/56450/West-Berkshire-Council-Strategy-2023-2027/pdf/WBC_Strategy_Sep_23_Final.pdf?m=1695826265037
The Local Transport Plan 2011-2026 | https://www.westberks.gov.uk/media/36911/Local-Transport-Plan-2011-2026/pdf/Local_Transport_Plan_2011-2026.pdf?m=1575546429557
Waste strategy | West Berkshire Waste Management Strategy 2025-2032 - West Berkshire Council
The Emerging Local Plan | Examination of the West Berkshire Local Plan Review 2022-2039 - West Berkshire Council
West Berkshire Council Tree Policy | Not yet published
The Parking Strategy | Due to be published in Summer 2025